U.S. Army Corps of Engineers, Pittsburgh                                                              10 August 2005

Operations Division

MEMORANDUM FOR Waterways Association of Pittsburgh

River Terminal Operators Association

SUBJECT:  August 2005 Meeting

##### ITEMS OF INTEREST TO NAVIGATION

1.  LOCK CLOSURES AND DELAYS - The following is the schedule of lock closures and delays through 21 October 2005.

New Cumberland L/D, Ohio River - The U.S. Army Corps of Engineers Repair Fleet closed and dewatered the small 110-ft x 600-ft lock chamber to repair the lock gates, sills and gate anchorages; and also to repair the service bridge lift span over the upstream end of the small chamber.  The job began on 12 July 2005 and all work is expected to be complete by

2 September 2005.  The small chamber will be closed for this 53-day work period.  The large 110-ft x 1200-ft lock chamber will be open to navigation interests with only minor delays expected.  (Reference Notice to Navigation Interests No. 05-12)

Lock 3, Monongahela River - The U.S. Army Corps of Engineers will close both 56-ft lock chambers from 8:00 AM thru 4:00 PM on Tuesday, 16 August 2005 to replace deteriorated hydraulic lines on the land wall and middle wall that control the gate and valve operating machinery.  No river traffic will be able to pass through Lock 3 during this 8-hour work period.  (Reference Notice to Navigation Interests No. 05-24)

Pike Island L/D, Ohio River - The U.S. Army Corps of Engineers Repair Fleet will make repairs to the river wall filling valve in the 110-ft x 1200-ft river chamber.  Work is scheduled to begin on 3 October 2005 and will be complete by 21 October 2005.  The large 110-ft x 1200-ft lock chamber will be open during the repair work, except as follows.  The large 110-ft x 1200-ft lock chamber will be closed for two periods, not to exceed 24-hours each, during the removal of the existing valve and during the installation of the new valve.  Additional large lock chamber closures up to 4 hours will occur periodically during the job to move the valve parts and equipment.  During the intermittent closures of the large lock chamber, all traffic will be passed through the small 110-ft x 600-ft lock chamber with a double lockage being the maximum acceptable tow.  Boat locking order will be determined by arrival time at Pike Island L/D, Ohio River.  (Reference Notice to Navigation Interests No. 05-22)

2.  RECOMMENDED INTERNET SITES - The following sites are recommended for the most up-to-date navigation information.

a. Daily Navigation Conditions:

www.lrd-wc.usace.army.mil/text/pitrpti.txt

Operations Division

SUBJECT:  August 2005 Meeting

b. Current River Conditions:

wmw.lrp.usace.army.mil/current/

c. District Navigation Notices:

www.lrd.usace.army.mil/navigation/notice/

3.  OTHER ITEMS OF INTEREST

A hydrographic survey (soundings) was taken of the area at approximate Mile 19.7, Monongahela River (at Peters Creek) to define the quantity of material to be removed; and sediment sampling and testing of materials to be dredged has been completed.  A contract for dredging at the mouth of Peters Creek will be awarded by the end of this week (10-12 August) with an expected start of dredging activity in 2-3 weeks.  Once the dredging at Peters Creek

is complete, the contractor will move his fleet to the lower Ohio River in the Pittsburgh District and begin dredging activity at Hannibal, Pike Island and New Cumberland Locks and Dams.  A scheduled timeframe for dredging these Ohio River projects has not yet been developed; we will provide a timeline by the next Waterways Association meeting in September.

As part of the Lower Mon River Project, five (5) dikes are to be constructed in the upstream approach to Braddock L/D, Mile 11.3, Monongahela River.  The Corps of Engineers investigated construction of these flow control dikes at the current intermediate pool elevation of El. 721.8 and concluded that the dikes could be constructed at this intermediate pool level without any adverse hydraulic effects.  The tops of the stone dikes are to be constructed to El. 708.7 providing a freeboard of 13.1 feet over the top of the dikes at the current intermediate operating pool.  With consideration of allowable tolerance for stone placement underwater, we would expect to have no local high spots shallower than 12.5 feet at the intermediate operating pool level of El. 721.8.  This work, when complete, will mitigate outdrafts in the upstream approach to the locks during high water events.  It is anticipated that the dikes may be constructed in the October-December 2005 timeframe utilizing one 10-hour shift each day for approximately 2 months.  The Corps of Engineers contractor will be required to have a helper towboat available to assist tows navigating the upper approach during the 10-hour shift each day that dike placement activities are taking place.

/signed/

RICHARD C. LOCKWOOD

Chief, Operations Division

2

# RIVER AND WEATHER CONDITIONS

Prepared for Waterways Assn. Of Pittsburgh Meeting 8/10/05

National Weather Service Forecast Office, Pittsburgh PA

For the latest river and weather forecasts--http://www.erh.noaa.gov/pbz

WEATHER RECAP

Rainfall averaged 2.75 – 3.5 inches, or about 0.75 – 1.5 inches below normal across the region.

At the Pittsburgh International Airport monthly precipitation was 4.33 inches, which is 0.37 of an inch below normal. Temperature averaged 2.5 degrees/day above normal.

For the first 9 days of August temperatures have been 3.6 degrees/day above normal and precipitation was 0.16 inches or 0.83 of an inch below normal.  Precipitation since 1 January has been 27.1 inches which is 2.98 inches above normal.

RIVER FLOWS

At the beginning of July flows on the main stem rivers were near normal, but  flows were below normal in many of the tributaries. The major rivers in the HSA fluctuated in a narrow range showing no large rises or prolonged recession throughout the month. Currently flows on the main stem rivers are 50 to 80 percent of the long term median flows.

HIGH WATER POTENTIAL

High water potential is low. Groundwater levels are lowering. Runoff potential is normal.  A widespread 3.0 to 3.5 inches of rain in 6 to 12 hours is needed to bring the major rivers to bankfull. Currently models are not indicating any widespread heavy rain events over the next two weeks.

WEATHER FORECAST

Today:  Partly cloudy and humid. High in the upper 80s.

Tonight:  20 percent chance of thunderstorms. Low in the upper 60s.

Thursday:  Partly cloudy. High near 85.

Thursday Night:  Partly cloudy. Low near 65.

Friday:  30 percent chance of afternoon thunderstorms. High near 85.

Friday Night:  40 percent chance of thunderstorms. Low in the upper 60s.

Saturday:  50 percent chance of thunderstorms. High near 85.

Saturday Night:  50 percent chance of thunderstorms. Low in the upper 60s.

Sunday:  50 percent chance of thunderstorms. High near 85.

Monday:  30 percent chance of thunderstorms. Low near 65. High near 83.

Tuesday:  Partly cloudy. Low in the lower 60s. High in the lower 80s.

The 8 to 14 day forecast is for above near normal temperatures and rainfall to be above normal in the Monongahela River basin and near normal elsewhere.

The Sep-Oct-Nov Outlook is for near normal temperature and precipitation.