## Slide 1
Fleet
Northern Area FRM
Quality
Notes
Southern Area FRM
Quality
Notes
Allegheny River L/D
Ohio River L/D
Dam
Dam
# Oper
Notes:
Lock (P)
Lock (A)
East Branch
Kinzua
Berlin
Shenango
Tionesta
Woodcock
Mosquito
MJ Kirwan
Union City
Control
Pittsburgh District Operations Readiness
Stonewall
Crooked Creek
Youghiogheny
Tygart West ringjet valve out of operation
Loyalhanna
Conemaugh
Mahoning
Control
Lock 9
Lock 8
Lock 7
Lock 6
Lock 5
Lock 4
C.W. Bill Young
Lock 2
Dashields
Emsworth Lock (P) RP (05-Jul-16)
14/14
8/10 Gate 3 (30 Jan 14), Gate 5 Construction
Montgomery
10/11 Lock (A) (10 Mar 15), Dam Gate 10 out of operation (15 Jun 15)
New Cumberland
9/9
Pike Island
As of 05 August 2016 – 1500 hrs
Gates
Monongahela River L/D
Hildebrand
Grays Landing
Hannibal
Opekiska
4/4
Morgantown
6/6 IMTS LOS 3
Point Marion
6/6
Maxwell Dam Gate 3 Out of Service (8-Jun-16)
4/5
Lock 4
5/5
Lock 3
Braddock 4/4
IMTS LOS 6 Commercial Lockage by Appointment Only
Fully Operational
Restricted Operations
Out of Operation
Unclassified
FOUO
RP/Fleet
RP
RP
LRP Top “System” Issues:
05 August, 2016
Issue: O&M – Montgomery L/D dam
Status: Contract expected for fabrication of two additional lift gates by EOY. Contract currently in process for installation of two lift gates with an option for installation of a third. LRP will continue to budget for fabrication and installation of dam gates in FY17 and FY18. RVD 06-16.
Issue: CG - Lower Mon Project
Status: Need a viable strategy dealing with how should the #2 IMTS priority project be funded. Since project completion date has been extended several years, LRP will continue to submit annual budget packages to keep the lock operational. RVD 01-14.
Issue: Dam Safety - East Branch Dam Safety Project
Status: Construction on the platform fill continues. Hauling of stone continues on both day and night shifts. RVD 06-15.
Issue: O&M - Upper Mon and Upper Allegheny service reduction iaw Standard Levels of Service
Status: As Opekiska, Hildebrand and Morgantown move to “Caretaker” status, can we execute a viable PPP?
Issue: O&M - Upper Mon and Upper Allegheny service reduction Standard Levels of Service
Status: IMTS LOS 6 Locks and Dams. LRP is working on developing standards for maintenance, security, safety, and environmental compliance at these facilities. RVD 01-14.
Entire System
Issue: O&M Improvement Plan
Status: Finish improvement plan w/ finalized PMP and running, prioritized 1-n list. RVD 01-14.
6/6
Repair Fleet
IMTS LOS 6 Commercial Lockage by Appointment Only
IMTS LOS 1 - Hours 24/7/365
IMTS LOS 2 - Hours 0700 – 2300, 7/365